## Sheet1
Product Backlog Item (PBI) | Acceptance Criteria | Definition of Done | Effort | PBI Author(s)
As a product owner, I want our voting system to handle the Instant Runoff (IR) Voting election since the Secretary of State asked for it. | The system determins the right winning candidate using the IR voting algorithm and ties between candidates are broken fairly. Code should be able to run on CSE lab machines. | Implementation, Unit and System tests are thorough and complete | Medium | Jashwin Acharya, Carlos Chasi-Mejia, Vincent Hoang and Steve Petzold
As a product owner, I want our voting system to handle the Open Party List (OPL) Voting election since the Secretary of State asked for it. | The system determins the right winning party and candidate using the OPL voting algorithm and ties between candidates are broken fairly. Code should be able to run on CSE lab machines. | Implementation, Unit and System tests are thorough and complete | Medium | Jashwin Acharya, Carlos Chasi-Mejia, Vincent Hoang and Steve Petzold
As an election official, I want the ballot calculations to be as hands-off as possible for ease of use. | The only thing asked is the name of the election file(s) and the date(s) of the election. Code should be able to run on CSE lab machines. | The election file(s) and date(s) are accepted by the system and ballot calculations are smoothly performed. | Small | Jashwin Acharya, Carlos Chasi-Mejia, Vincent Hoang and Steve Petzold
As an election official, I want the voting system to handle the Multiple Popularity Only (MPO) voting election since the Secretary of State asked for it and we want the ability to declare multiple winners. | The system determines the right winners based on the MPO voting algorithm by considering all candidates tied with the most number of votes. The algorithm should provide fair and unbiased results. Code should be able to run on CSE lab machines. | Documentation, Implementation, Unit and System tests are thorough and complete. | Large | Jashwin Acharya, Carlos Chasi-Mejia, Vincent Hoang and Steve Petzold
As an election official, I would like to see the winning Candidate(s) and Party information as well as final voting statistics of all candidates in the MPO election so that constituents who voted know how well their candidate did in the election. | All candidate and party statistics are calculated and displayed correctly on screen along with the winner's information. Code should be able to run on CSE lab machines. | MPO stats calculations is correctly implemented and thoroughly tested via unit tests and manual/system tests | Small | Jashwin Acharya, Carlos Chasi-Mejia, Vincent Hoang and Steve Petzold
As an election official, I want the system to identify IRV ballots that have less than half the candidates ranked so that invalid ballots can be removed from the election | Invalid ballots are successfully removed during ballot processing. Code should be able to run on CSE lab machines. | Implementation, Unit and System tests are thorough and complete for removing invalid ballots. | Small | Jashwin Acharya, Carlos Chasi-Mejia, Vincent Hoang and Steve Petzold
As an election official, I want the system to store invalid IRV ballots into a separate directory for auditing purposes | Invalid ballots are successfully stored in a newly created directory if it doesn't exist; otherwise, a new directory is created. Code should be able to run on CSE lab machines. | Ensure that the directory is created and contains invalid ballots that have the date of the election as part of their file name for auditing purposes. | Small | Jashwin Acharya, Carlos Chasi-Mejia, Vincent Hoang and Steve Petzold
As an election official, I want the ability to choose multiple election files using a GUI so that I can bring in files from different balloting locations. | The voting system should successfully be able to process multiple files. Code should be able to run on CSE lab machines. | GUI is implemented and allows the user to navigate the system directory and choose multiple files for processing. | Medium | Jashwin Acharya, Carlos Chasi-Mejia, Vincent Hoang and Steve Petzold
As an election official, I want the statistics of each redistribution round in an IR Voting system displayed on screen once all ballot calculations are performed since the secretary of state and media personnel would like to know how all the candidate votes were redistributed. | All redistribution round information is displayed on the screen to the user along with the name of the winner after redistribution is complete. Code should be able to run on CSE lab machines. | Ensure that the vote statistics for each redistribution round are correctly calculated via unit tests, and manual testing should also be performed to ensure the data is correctly formatted on screen. | Medium | Jashwin Acharya, Carlos Chasi-Mejia, Vincent Hoang and Steve Petzold