## Sheet1
PBI | Effort | Tasks | Not Started | In Progress | Complete
As a product owner, I want our voting system to handle the Instant Runoff (IR) Voting election since the Secretary of State asked for it. | Medium | Task #1: Implement tie breaker for lowest vote candidates during redistribution. Task #2: Implement and document new unit tests for IR Voting class. Task #3: Implement and document new system tests for IR Voting class. | Task #1 Task #2 Task #3
As a product owner, I want our voting system to handle the Open Party List (OPL) Voting election since the Secretary of State asked for it. | Medium | Task #1: Implement a check to not give seats to a party anymore once a party has received the number of seats equal to the number of candidates. Task #2: Implement a redistribution of the remaining seats to all parties again once every party has received a remaining seat after the second round and there are still seats left. Task #3: Implement and document new unit tests for OPL Voting class. Task #4: Implement and document new system tests for OPL Voting class. | Task #1 Task #2 Task #3 Task #4
As an election official, I want the ballot calculations to be as hands-off as possible for ease of use. | Small | Task #1: Implement File Parsing Logic to parse MPO Election File. Task #2: Implement and document unit tests for MPO file parsing functionality. | Task #1 Task #2
As an election official, I want the voting system to handle the Multiple Popularity Only (MPO) voting election since the Secretary of State asked for it and we want the ability to declare multiple winners. | Large | Task #1: Implement ballot parsing logic for MPO. Task #2: Implement Candidate information parsing logic for MPO. Task #3: Implement Seat allocation logic for candidates and parties for MPO. Task #4: Document MPO Voting class methods and member variables. Task #5: Implement audit file writing logic for seat allocation in MPO Voting class. Task #5: Implement and document unit tests for MPO Voting class. Task #6: Implement and document system tests for MPO Voting class. | Task #1 Task #2 Task #3 Task #4 Task #5 Task #6
As an election official, I would like to see the winning Candidate(s) and Party information as well as final voting statistics of all candidates in the MPO election so that constituents who voted know how well their candidate did in the election. | Small | Task #1: Implement logic for displaying final vote statistics for all candidates in the MPO election. Task #2: Implement and document system tests for displaying final vote statistics for MPO. | Task #1 Task #2