## Sheet1
PBI | Acceptance Criteria | Definition of done | Effort | Tasks | Not Started | In Progress | Complete
As a product owner, I want our voting system to handle the Instant Runoff (IR) Voting election since the Secretary of State asked for it. | The system determins the right winning candidate using the IR voting algorithm and ties between candidates are broken fairly. Code should be able to run on CSE lab machines. | Implementation, Unit and System tests are thorough and complete | Medium | Task #1: Implement tie breaker for lowest vote candidates during redistribution. Task #2: Implement and document new unit tests for IR Voting class. Task #3: Implement and document new system tests for IR Voting class. | Task #1 Task #2 Task #3 |  | Task #1 - Jashwin Task #2 - Jashwin Task #3 - Jashwin
As a product owner, I want our voting system to handle the Open Party List (OPL) Voting election since the Secretary of State asked for it. | The system determins the right winning party and candidate using the OPL voting algorithm and ties between candidates are broken fairly. Code should be able to run on CSE lab machines. | Implementation, Unit and System tests are thorough and complete | Medium | Task #1: Implement a check to not give seats to a party anymore once a party has received the number of seats equal to the number of candidates. Task #2: Implement a redistribution of the remaining seats to all parties again once every party has received a remaining seat after the second round and there are still seats left. Task #3: Implement and document new unit tests for OPL Voting class. Task #4: Implement and document new system tests for OPL Voting class. | Task #1 Task #2 Task #3 Task #4 |  | Task #1 - Vincent Task #2 - Vincent Task #3 - Vincent Task #4 - Vincent
As an election official, I want the ballot calculations to be as hands-off as possible for ease of use. | The only thing asked is the name of the election file(s) and the date(s) of the election. Code should be able to run on CSE lab machines. | The election file(s) and date(s) are accepted by the system and ballot calculations are smoothly performed. | Small | Task #1: Implement File Parsing Logic to parse MPO Election File. Task #2: Implement and document unit tests for MPO file parsing functionality. | Task #1 Task #2 |  | Task #1 - Carlos Task #2 - Carlos
As an election official, I want the voting system to handle the Multiple Popularity Only (MPO) voting election since the Secretary of State asked for it and we want the ability to declare multiple winners. | The system determines the right winners based on the MPO voting algorithm by considering all candidates tied with the most number of votes. The algorithm should provide fair and unbiased results. Code should be able to run on CSE lab machines. | Documentation, Implementation, Unit and System tests are thorough and complete. | Large | Task #1: Implement ballot parsing logic for MPO. Task #2: Implement Candidate information parsing logic for MPO. Task #3: Implement Seat allocation logic for candidates and parties for MPO. Task #4: Document MPO Voting class methods and member variables. Task #5: Implement audit file writing logic for seat allocation in MPO Voting class. Task #5: Implement and document unit tests for MPO Voting class. Task #6: Implement and document system tests for MPO Voting class. | Task #1 Task #2 Task #3 Task #4 Task #5 Task #6 | Task #4 - Steve Task #5 - Steve | Task #1 - Jashwin Task #2 - Steve Task #3 - Jashwin
As an election official, I would like to see the winning Candidate(s) and Party information as well as final voting statistics of all candidates in the MPO election so that constituents who voted know how well their candidate did in the election. | All candidate and party statistics are calculated and displayed correctly on screen along with the winner's information. Code should be able to run on CSE lab machines. | MPO stats calculations is correctly implemented and thoroughly tested via unit tests and manual/system tests | Small | Task #1: Implement logic for displaying final vote statistics for all candidates in the MPO election. Task #2: Implement and document system tests for displaying final vote statistics for MPO. | Task #1 Task #2 | Task #1 - Carlos